##### Rycon Construction, Inc.

##### Public Storage Fairfax

Fairfax, VA

# Project Schedule Narrative (Update 05)

## Schedule File: PSFVA-UP05-R0

## Data Date: January 31, 2026

## Submitted: February 5, 2026

Point of Contact: Emily Antico

Senior Project Manager, Aegis Project Controls

##### (202) 768 - 3049, eantico@consultaegis.com

Contents

Project Schedule Narrative (Update 05)	1

Schedule File: PSFVA-UP05-R0	1

Data Date: January 31, 2026	1

Submitted: February 5, 2026	1

Project Overview	2

Critical Path	3

Activity Progress this Period	4

Schedule Modifications	4

Owners Comments	5

Weather	5

Conclusion	5

Attachments	5

# Project Overview

Attached is the January 2026 schedule update which contains standard maintenance changes regarding means and methods, reasonable logic alterations, along with the actual progress from January 1, 2026, through January 31, 2026. The schedule is demonstrating a Substantial Completion date of August 12, 2026, which is seven (7) calendar days ahead of the schedule when compared to the Contract Completion Date.

| Activity ID | Milestone | BASELINE | Update 05 | Total ∆ |
| --- | --- | --- | --- | --- |
| MIL1020 | SUBSTANTIAL COMPLETION | 19-Aug-26 | 12-Aug-26 | 7 |

1.1: Milestone Progress Table

# Critical Path

The primary critical path in this schedule update is driven by Fragnet 001 – Weather Delays – Site Shutdown Due to Ice and Road Conditions. Once the Fragnet 001 is completed the path moves to the Main Building – Superstructure – Fourth Floor – Prep & Pour SOD – 5th Floor. Once the Prep & Pour is completed the path moves to the Main Building – Interior Finishes – Fourth Floor - Fire Proofing Structural Steel and Main Building – Superstructure – Fifth Floor – Structural Steel Columns & Beams. Once those activities are completed the path moves to Main Building – Exterior Finishes – Exterior Sheathing – 4th Floor. Once the Sheathing is completed the path moves to Main Building – Superstructure – Fourth Floor – Exterior & Interior Framing. Once the Framing is completed the path moves to the Main Building – Exterior Finishes – Perimeter Waterproofing West Elevation (Excluding 5th Floor). Once the Waterproofing is completed the path continues to Main Building – Superstructure – Fifth Floor - Framing & Metal Decking – Roof. Once Framing of the 5th Floor is completed the path continues with the Main Building – Exterior Finishes – Brick West Elevation (Excluding 5th Floor) and Main Building – Roofing – Roof Insulation & TPO. Once both those activities are completed the path moves to the Main Building – Interior Finishes – Fifth Floor – Fire Proofing Structural Steel. Once the 5th Floor Fire Proofing is completed the path moves to Main Building – Exterior Finishes – Exterior Sheathing – 5th Floor. Once the Sheathing is completed on the 5th Floor the rest of the 5th Floor Superstructure - Framing - can be completed. Once the 5th Floor is completed with the Superstructure the path continues with the rest of the Main Building – Exterior Finishes. Once the Main Building Exterior Finishes are completed the path continues with Main Building – Site Work. Once Main Building – Site Work is completed the path finishes with Final Inspections & Closeout ahead of Final Completion on September 4, 2026.

2.1: Critical Path

# Activity Progress this Period

There were thirty (30) activities completed during the update period. 54% of planned near critical activities were completed. 83% of planned critical activities were completed. 29% of planned non-critical activities were completed.

# Schedule Modifications

In summary, the following changes were incorporated for this month’s update. Please see the attached Excel Schedule Comparison Report for specific modifications.

- Added Activities:

  - Four (4) activities were added to the schedule in this update period.

- Deleted Activities:

  - No activities were removed from the schedule in this update period.

- Changed Activity Names:

  - No activity description was changed in this update period.

- Changed Original Durations:

  - Three (3) activities experienced a change in their original duration in this update period.

- Addition of Logic Relationships:

  - Twenty-Two (22) relationships were added to the schedule in this update period.

- Deletion of Logic Relationships:

  - Five (5) relationships were deleted from the schedule in this update period.

# Owners Comments

# Weather

In this update period, the project experienced ____ (X) weather impacted days.

# Conclusion

This update period contains progress from January 1, 2026, through January 31, 2026. The schedule is demonstrating a Substantial Completion date of August 12, 2026, which is seven (7) days ahead of the schedule when compared to the Contract Completion Date.

# Attachments

- PSFVA-UP05-R0 – XER File

- All Activities

- Comparison Report

- Critical Lookahead

- Longest Path

- Remaining Activities